## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.
REVISAR EL NÚMERO DE ENTREGAS ESTE CURSO!!!!!
La columna estatus es redundante con Execution Period. Poner autocalculada.
Poner filtros en las columnas.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 1961.25
|  | Actual: | 1944.42
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 1 | Manager | Initialise repository |  | 2026-02-09 12:30 | 2026-02-09 12:50 | Completed | 0.5 | 0.333 | 25 | 16.65 | Initialise the workgroup repository at GitHub
2 | T0002/M | Management | Student 1 | Manager | Write report |  | 2026-02-09 13:00 | 2026-02-09 14:00 | Completed | 1 | 1 | 50 | 50 | Prepare a chartering report
3 | T0003/D | Development | Student 3 | Developer | Customise the starter |  | 2026-02-10 11:00 | 2026-02-10 14:30 | Completed | 2 | 3.5 | 50 | 87.5 | Customise the starter project
4 | T0004/D | Development | Student 3 | Developer | Customise the starter | T0003/D | 2026-02-10 11:00 | 2026-02-10 14:00 | Completed | 1.5 | 3 | 37.5 | 75 | Customise key files
5 | T0005/D | Development | Student 3 | Developer | Customise the starter | T0003/D | 2026-02-10 14:00 | 2026-02-10 14:20 | Completed | 0.25 | 0.33 | 6.25 | 8.25 | Create the databases
6 | T0006/D | Development | Student 3 | Developer | Customise the starter | T0003/D | 2026-02-10 14:20 | 2026-02-10 14:30 | Completed | 0.25 | 0.17 | 6.25 | 4.25 | Launch the project
7 | T0007/M | Management | Student 1 | Manager | Make plans |  | 2026-02-15 10:06 | 2026-02-15 10:32 | Completed | 0.5 | 0.43 | 25 | 21.5 | Instantiate, share and complete a planning document
8 | T0008/D | Development | Student 1 | Developer | Implement feature | [8 empty] | S1/1) Implement the data model that is sketched in file “Model-C01.uxf”
9 | T0009/D | Development | Student 1 | Developer | Implement feature | T0008/D | 2026-02-15 11:12 | 2026-02-15 12:25 | Completed | 1 | 1.22 | 25 | 30.5 | Implement entites and roles and their relationships
10 | T0010/D | Development | Student 1 | Developer | Implement feature | T0008/D | 2026-02-22 10:46 | 2026-02-22 11:44 | Completed | 1 | 1 | 25 | 25 | Implement restrictions and validations
11 | T0011/D | Development | Student 2 | Developer | Implement feature | [8 empty] | S2/1) Implement the data model that is sketched in file “Model-C02.uxf”.
12 | T0012/D | Development | Student 2 | Developer | Implement feature | T0011/D | 2026-02-22 23:38 | 2026-02-23 00:46 | Completed | 1 | 1.13 | 25 | 28.25 | Implement entites and roles and their relationships
13 | T0013/D | Development | Student 2 | Developer | Implement feature | T0011/D | 2026-02-28 12:03 | 2026-02-28 13:06 | Completed | 1 | 1.05 | 25 | 26.25 | Implement restrictions and validations
14 | T0014/D | Development | Student 3 | Developer | Implement feature | [8 empty] | S3/1) Implement the data model that is sketched in file “Model-C03.uxf”.
15 | T0015/D | Development | Student 3 | Developer | Implement feature | T0014/D | 2026-02-15 19:26 | 2026-02-15 20:47 | Completed | 1 | 1.35 | 25 | 33.75 | Implement entites and roles and their relationships
16 | T0016/D | Development | Student 3 | Developer | Implement feature | T0014/D | 2026-02-23 15:34 | 2026-02-23 16:29 | Completed | 1 | 1 | 25 | 25 | Implement restrictions and validations
17 | T0017/D | Development | Student 4 | Developer | Implement feature | [8 empty] | S4/1) Implement the data model that is sketched in file “Model-C04.uxf”.
18 | T0018/D | Development | Student 4 | Developer | Implement feature | T0017/D | 2026-02-16 08:40 | 2026-02-16 09:42 | Completed | 1 | 1.03 | 25 | 25.75 | Implement entites and roles and their relationships
19 | T0019/D | Development | Student 4 | Developer | Implement feature | T0017/D | 2026-02-24 15:22 | 2026-02-24 16:31 | Completed | 1 | 1.15 | 25 | 28.75 | Implement restrictions and validations
20 | T0020/D | Development | Student 5 | Developer | Implement feature | [8 empty] | S5/1) Implement the data model that is sketched in file “Model-05.uxf”.
21 | T0021/D | Development | Student 5 | Developer | Implement feature | T0020/D | 2026-02-15 20:55 | 2026-02-15 23:12 | Completed | 1 | 2.17 | 25 | 54.25 | Implement entites and roles and their relationships
22 | T0022/D | Development | Student 5 | Developer | Implement feature | T0020/D | 2026-02-24 15:15 | 2026-02-24 16:10 | Completed | 1 | 0.92 | 25 | 23 | Implement restrictions and validations
23 | T0023/D | Development | Student 5 | Developer | Implement feature | T0020/D | 2026-02-24 16:12 | 2026-02-24 16:30 | Completed | 0.5 | 0.3 | 12.5 | 7.5 | Create the sample data required to create two administrators
24 | T0024/D | Development | ALL | Developer | Implement feature |  | 2026-02-23 09:11 | 2026-02-23 09:30 | Completed | 0.1 | 0.3167 | 2.5 | 7.9175 | Delete "//" in custom validations & fixed Temporal/Date
25 | T0025/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-08 11:51 | 2026-03-08 14:54 | Completed | 3 | 3 | 75 | 75 | S1/2) List published inventions (Principal)
26 | T0026/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-15 20:31 | 2026-03-15 20:52 | Completed | 2 | 0.35 | 50 | 8.75 | S1/3) Acquire Inventor role (authenticated Principal)
27 | T0027/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-12 10:41 | 2026-03-15 20:02 | Completed | 3 | 4 | 75 | 100 | S1/4) CRUD Inventions and Parts (Inventor)
28 | T0028/D | Development | Student 1 | Developer | Implement feature |  | 2026-03-15 20:25 | 2026-03-15 20:29 | Completed | 1 | 0.067 | 25 | 1.675 | S1/5) UI in English and Spanish
29 | T0029/D | Development | Student 1 | Developer | Test feature informally |  | 2026-03-03 10:40 | 2026-03-03 12:09 | Completed | 1.5 | 1.5 | 37.5 | 37.5 | S1/6) Test the requirements
30 | T0030/R/ | Revision | ALL | Student | Attend lecture |  | 2026-02-09 08:30 | 2026-02-09 10:20 | Completed | 1.83 | 1.83 | 0 | 0 | Follow-up
31 | T0031/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-22 10:27 | 2026-02-22 10:46 | Completed | 0.5 | 0.3167 | 12.5 | 7.9175 | Implement the constraints that are sketched in "Model-CG.uxf"
32 | T0032/M | Management | Student 1 | Manager | Make re-plannings |  | 2026-02-23 09:36 | 2026-02-23 09:52 | Completed | 0.5 | 0.2667 | 25 | 13.335 | Re-plan report
33 | T0033/R/ | Revision | ALL | Student | Attend lecture |  | 2026-02-12 10:40 | 2026-02-12 12:30 | Completed | 1.83 | 1.83 | 0 | 0 | Theory class
34 | T0034/R/ | Revision | ALL | Student | Attend lecture |  | 2026-02-16 08:30 | 2026-02-16 10:20 | Completed | 1.83 | 1.83 | 0 | 0 | Follow-up
35 | T0035/R/ | Revision | ALL | Student | Attend lecture |  | 2026-02-19 10:40 | 2026-02-19 12:30 | Completed | 1.83 | 1.83 | 0 | 0 | Theory class
36 | T0036/R/ | Revision | ALL | Student | Attend lecture |  | 2026-02-23 08:30 | 2026-02-23 10:20 | Completed | 1.83 | 1.83 | 0 | 0 | Follow-up
37 | T0037/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-08 23:25 | 2026-03-09 00:33 | Completed | 3 | 1.13 | 75 | 28.25 | S2/2) Browse campaigns
38 | T0038/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-16 00:17 | 2026-03-16 00:59 | Completed | 2 | 0.7 | 50 | 17.5 | S2/3) Spokesperson role
39 | T0039/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-15 21:34 | 2026-03-16 00:16 | Completed | 3 | 2.3 | 75 | 57.5 | S2/4) Manage campaigns
40 | T0040/D | Development | Student 2 | Developer | Implement feature |  | 2026-03-16 00:59 | 2026-03-16 01:02 | Completed | 1 | 0.05 | 25 | 1.25 | S2/5) UI internationalization
41 | T0041/D | Development | Student 2 | Developer | Test feature informally |  | 2026-03-08 22:27 | 2026-03-08 23:24 | Completed | 1.5 | 0.95 | 37.5 | 23.75 | S2/6) Test data
42 | T0042/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-09 21:00 | 2026-03-09 23:09 | Completed | 3 | 2.15 | 75 | 53.75 | S3/2) List Strategies, Tactics and frundaiser's Profile
43 | T0043/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-15 22:40 | 2026-03-15 23:30 | Completed | 2 | 1 | 50 | 25 | S3/3) What any authenticathed principal must be able to do
44 | T0044/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-12 17:30 | 2026-03-15 23:30 | Completed | 3 | 5.5 | 75 | 137.5 | S3/4) What a principal with role fundraiser must be able to do
45 | T0045/D | Development | Student 3 | Developer | Implement feature |  | 2026-03-15 23:30 | 2026-03-15 23:34 | Completed | 1 | 0.07 | 25 | 1.75 | S3/5) UI internationalised
46 | T0046/D | Development | Student 3 | Developer | Test feature informally |  | 2026-02-28 18:15 | 2026-02-28 20:00 | Completed | 1.5 | 1.75 | 37.5 | 43.75 | S3/6) Sample data to test requirements
47 | T0047/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-12 17:33 | 2026-03-12 20:21 | Completed | 3 | 2.74 | 75 | 68.5 | S5/2) Viewing and management of published audit reports
48 | T0048/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-16 01:08 | 2026-03-16 04:22 | Completed | 2 | 3.23 | 50 | 80.75 | S5/3) Role acquisition and profile update for auditors
49 | T0049/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-15 20:56 | 2026-03-16 01:04 | Completed | 3 | 4.13 | 75 | 103.25 | S5/4) Audit report management and publication process
50 | T0050/D | Development | Student 5 | Developer | Implement feature |  | 2026-03-16 | 2026-03-16 00:04 | Completed | 1 | 0.067 | 25 | 1.675 | S5/5) UI internationalised
51 | T0051/D | Development | Student 5 | Developer | Test feature informally |  | 2026-03-04 11:02 | 2026-03-04 11:52 | Completed | 1.5 | 0.83 | 37.5 | 20.75 | S5/6) Sample data to test requirements
52 | T0052/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-10 16:54 | 2026-03-12 20:47 | Completed | 3 | 3.23 | 75 | 80.75 | S4/2) List Sponsorship, Donations published
53 | T0053/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-16 16:20 | 2026-03-16 18:49 | Completed | 2 | 2.46 | 50 | 61.5 | S4/3) Acquire sponsor role
54 | T0054/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-15 08:35 | 2026-03-16 15:16 | Completed | 3 | 4.25 | 75 | 106.25 | S4/4) CRUD of Sponsorship
55 | T0055/D | Development | Student 4 | Developer | Implement feature |  | 2026-03-16 18:48 | 2026-03-16 19:03 | Completed | 1 | 0.07 | 25 | 1.75 | S4/5) UI internationalised
56 | T0056/D | Development | Student 4 | Developer | Test feature informally |  | 2026-03-09 01:03 | 2026-03-09 03:15 | Completed | 1.5 | 2.2 | 37.5 | 55 | S4/6) Sample data to test requirements
57 | T0057/R/ | Revision | ALL | Student | Attend lecture |  | 2026-03-02 08:30 | 2026-03-02 10:20 | Completed | 1.83 | 1.83 | 0 | 0 | Follow-up
58 | T0058/R/ | Revision | ALL | Student | Attend lecture |  | 2026-03-05 10:40 | 2026-03-05 12:30 | Completed | 1.83 | 1.83 | 0 | 0 | Theory class
59 | T0059/D | Development | Student 1 | Developer | Other (Describe) |  | 2026-03-08 10:34 | 2026-03-08 11:45 | Completed | 1 | 1 | 25 | 25 | Update Workspace to REV3
60 | T0060/R/ | Revision | ALL | Student | Attend lecture |  | 2026-03-12 10:40 | 2026-03-12 12:30 | Completed | 1.83 | 1.83 | 0 | 0 | Theory class
61 | T0061/R/ | Revision | ALL | Student | Attend lecture |  | 2026-03-16 08:30 | 2026-03-16 10:20 | Completed | 1.83 | 1.83 | 0 | 0 | Follow-up
62 | T0062/D | Development | ALL | Developer | Other (Describe) |  | 2026-03-16 08:45 | 2026-03-16 09:00 | Completed | 0.3 | 0.25 | 7.5 | 6.25 | Delete ENFORCE_FUTURE & dates validation only when publishing
63 | T0063/D | Development | Student 3 | Developer | Other (Describe) |  | 2026-03-16 08:30 | 2026-03-16 08:45 | Completed | 0.3 | 0.25 | 7.5 | 6.25 | Fix ticker pattern
64 | T0064/D | Development | Student 3 | Developer | Other (Describe) |  | 2026-03-16 11:00 | 2026-03-16 11:58 | Completed | 1 | 1 | 25 | 25 | Fix validations in student 3
65 | T0065/D | Development | Student 1 | Developer | Other (Describe) |  | 2026-03-17 10:45 | 2026-03-17 11:14 | Completed | 1 | 0.5 | 25 | 12.5 | Fix date validation
66 | T0066/D | Development | Student 1 | Developer | Other (Describe) |  | 2026-03-18 08:36 | 2026-03-18 08:44 | Completed | 0.25 | 0.12 | 6.25 | 3 | Fix getMonthsActive
67 | T0067/D | Development | Student 3 | Developer | Other (Describe) |  | 2026-03-19 20:30 | 2026-03-19 21:34 | Completed | 1 | 1 | 25 | 25 | Fix internationalisation in Boolean and Select
68 | T0068/D | Development | Student 2 | Developer | Other (Describe) |  | 2026-03-20 00:15 | 2026-03-20 02:05 | Completed | 1 | 1.92 | 25 | 48 | Fix validations in student 2
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 468.75
|  | Actual: | 687.425
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 1 | Manager | Make plans |  | 2026-04-26 21:12 | 2026-04-27 00:04 | Completed | 2.5 | 2.75 | 125 | 137.5 | Rewrite requirements in analysis report and data model
2 | T0002/D | Development | Student 1 | Developer | Implement feature |  | 2026-04-27 08:40 | 2026-04-27 08:56 | Completed | 0.5 | 0.267 | 12.5 | 6.675 | Implement role Manager
3 | T0003/D | Development | Student 2 | Developer | Implement feature |  | 2026-04-28 14:56 | 2026-04-28 16:02 | Completed | 1 | 1.1 | 25 | 27.5 | Implement entity Project + additional constraints (keywords and dates)
4 | T0004/D | Development | Student 3 | Developer | Implement feature |  | 2026-04-27 08:50 | 2026-04-27 09:30 | Completed | 0.5 | 0.66 | 12.5 | 16.5 | Implement squad ProjectMember
5 | T0005/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-06 19:38 | 2026-05-07 23:51 | Completed | 2 | 4 | 50 | 100 | manager: CRUD projects + publish Projects
6 | T0006/D | Development | Student 5 | Developer | Implement feature |  | 2026-05-07 10:40 | 2026-05-07 11:49 | Completed | 1 | 1.15 | 25 | 28.75 | manager: create projectmembers
7 | T0007/D | Development | Student 3 | Developer | Implement feature |  | 2026-04-27 19:30 | 2026-05-05 13:27 | Completed | 1 | 3 | 25 | 75 | projectmember: Display projects + components
8 | T0008/D | Development | Student 2 | Developer | Implement feature |  | 2026-05-08 13:58 | 2026-05-08 17:00 | Completed | 1 | 3.04 | 25 | 76 | projectmember: add components to a project
9 | T0009/D | Development | Student 1 | Developer | Implement feature |  | 2026-05-03 23:43 | 2026-05-04 00:12 | Completed | 1 | 0.5 | 25 | 12.5 | Dashboard + effort
10 | T0010/D | Development | Student 5 | Developer | Implement feature |  | 2026-05-05 16:24 | 2026-05-05 18:11 | Completed | 1.5 | 1.78 | 37.5 | 44.5 | Sponsor/auditor attaching to a project
11 | T0011/D | Development | Student 4 | Developer | Implement feature |  | 2026-05-04 08:43 | 2026-05-06 19:38 | Completed | 1 | 2.5 | 25 | 62.5 | Advertisement
12 | T0012/D | Development | Student 1 | Developer | Other (Describe) |  | 2026-05-04 08:41 | 2026-05-04 09:35 | Completed | 1 | 1 | 25 | 25 | Sample and errata for Manager
13 | T0013/D | Development | Student 2 | Developer | Other (Describe) |  | 2026-05-04 08:42 | 2026-05-04 09:40 | Completed |  |  |  |  | Sample and errata for Project
14 | T0014/D | Development | Student 1 | Developer | Other (Describe) |  | 2026-05-05 10:37 | 2026-05-05 12:08 | Completed | 0.25 | 1.5 | 6.25 | 37.5 | Link components to projects on sample and errata (key:project on each component's csv)
15 | T0015/D | Development | Student 1 | Developer | Other (Describe) |  | 2026-05-04 09:35 | 2026-05-04 10:40 | Completed | 1 | 1 | 25 | 25 | Sample and errata for ProjectMembership and ProjectMember
16 | T0016/D | Development | Student 1 | Developer | Implement feature |  | 2026-05-06 09:40 | 2026-05-06 10:11 | Completed | 1 | 0.5 | 25 | 12.5 | ManagerDashboard feature
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O